OTOPAIR

Daniel’s Launch Roadmap & Sprint Plan

v5 — Aligned with Cross-Team Dependencies

March 28 – June 1, 2026  •  65 Days  •  9 Sprints

Prepared for: Daniel Chelala & Otopair Team

Meetings: Monday & Thursday Nights  •  Heavy Days: Sat–Mon

Team Launch: June 1, 2026  •  P0s Done: May 7  •  Ahmad’s Consumer App: May 14

# Executive Summary

This v5 roadmap aligns Daniel’s shop portal and admin plan with the cross-team dependency map from the March 30 analysis (Ahmad H. × Daniel C. × Waleed M.). Key changes from v3:

- Launch date restored to June 1 — per team decision #9. Ahmad’s May 14 is the consumer app internal milestone, not the team launch. Daniel and Waleed target June 1.

- P0 completion target stays May 7 — same aggressive P0 schedule from v3. All shop portal and admin P0 tickets done by end of Sprint 6.

- Sprints 7–9 restored — the 3.5 weeks between May 7 and June 1 are used for P1 tickets, integration testing with Ahmad’s consumer app, and launch prep. This was the buffer v3 cut.

- Cross-team dependencies mapped per sprint — each sprint now flags which Waleed deliverables Daniel depends on, and when Daniel’s output unblocks Waleed.

Current Status

| Workstream | Status | Remaining |
| --- | --- | --- |
| Shop Portal (Epic 2) | 2 done, 2 nearly done | 7 P0 tickets + 5 P1 tickets |
| Admin Pages (Epic 5) | 0 of 8 P0 done | 8 P0 + 2 post-launch |
| Consumer Mobile App | Build done (Ahmad’s lane) | QA + polish, Daniel’s Android lane |

# Cross-Team Dependency Map

Extracted from the March 30 cross-team analysis. These are the specific points where Daniel’s work intersects with Ahmad and Waleed.

Daniel Depends on Waleed

| When | Daniel’s Ticket | Waleed’s Item | Risk & Mitigation |
| --- | --- | --- | --- |
| Sprint 4 | 2.9 Job Actuals — variance calc | #4 Quotable Labor | Medium. If #4 not wired by Apr 17, Daniel builds variance form without baseline. Wire real data later. |
| Sprint 6 | 5.8 Vehicle Specs Review Queue | #2 Confidence, #5 Source | Low. #5 is DONE. #2 targeted for Apr 2. Should be cleared well before May 1. |

Waleed Depends on Daniel

| When | Daniel’s Ticket | Detail |
| --- | --- | --- |
| May 12–16 | 2.9/2.12 Job completion flow (Sprint 4) | Waleed needs mechanic verification for W4. Daniel ships this Apr 17–23. 3-week gap. No conflict. |

Daniel → Ahmad

- Integration testing: Ahmad’s consumer app stable by May 4 (his QA sign-off). Daniel’s integration testing is Sprint 8 (May 15–21). Ahmad’s app is ready 11 days before Daniel needs it. No conflict.

- Android: Android is Daniel’s lane per team decision #7. Ahmad’s iOS-only references noted. Daniel handles Android testing in Sprint 8–9.

# Phase Overview

| Phase | Dates | Focus | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | Mar 28 – Apr 9 | Schedule + Foundation | Schedule done, auth, onboarding, dashboard |
| Phase 2 | Apr 10 – Apr 23 | Team + Jobs Lifecycle | Team mgmt, jobs queue, actuals, mechanic dash |
| Phase 3 | Apr 24 – May 7 | Admin Panel | All admin P0 pages. ALL P0s DONE. |
| Phase 4 | May 8 – May 21 | P1 + Integration | P1 tickets, integration testing with consumer app |
| Phase 5 | May 22 – Jun 1 | QA + Launch | Final QA, Android, staging, Brooklyn shops, go-live |

# Weekly Sprint Breakdown

## Sprint 1: Mar 28 – Apr 2 — Schedule & Auth Lock  ✓

Status: Nearly complete. Finishing 2.7 cleanup and 2.3.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.7 | Day view — bug fixes | 0.5 | P0 | In progress |
| 2.7 | Day view — add/create new booking | 1 | P0 | Remaining |
| 2.7 | Week view — polish | 0.5 | P0 | Remaining |
| 2.7 | Month view — polish | 0.5 | P0 | Remaining |
| 2.3 | Portal Auth Isolation & Route Guards | 3 | P0 | Remaining |

Mon Mar 30 meeting: Schedule demo, all three views.

Thu Apr 2 meeting: 2.7 and 2.3 complete. Ready for Sprint 2.

⚠ Cross-team: Waleed targets #2 (confidence scores) by Thu Apr 2. If delivered, clears the 5.8 dependency early.

## Sprint 2: Apr 3 – Apr 9 — Onboarding & Dashboard

Goal: Shop registration wizard and owner dashboard.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.4 | Shop Registration & Onboarding Wizard | 8 | P0 | Fri–Tue (Apr 3–7) |
| 2.5 | Shop Owner Dashboard | 5 | P0 | Tue–Thu (Apr 7–9) |

Mon Apr 6 meeting: Onboarding wizard walkthrough.

Thu Apr 9 meeting: Dashboard live. Full onboarding → dashboard flow.

Scope guard: 2.4 is 8 pts. Timebox to 4 days. Core flow only.

⚠ Cross-team: Ahmad starts Home → Booking integration Apr 8. Stub data decision must be made by Apr 7 (team decision #5). Not blocking Daniel directly.

## Sprint 3: Apr 10 – Apr 16 — Team Management & Jobs Queue

Goal: Mechanic invite flow, team page, accept/decline jobs queue.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.6 | Mechanic Profile Management + Invite UI | 5 | P0 | Fri–Mon (Apr 10–13) |
| 2.8 | Accept/Decline Jobs Queue | 5 | P0 | Mon–Thu (Apr 13–16) |

Mon Apr 13 meeting: Invite mechanic, mechanic accepts, appears on team page.

Thu Apr 16 meeting: Jobs queue with accept/decline working.

⚠ Cross-team: Waleed’s Oto backend should be nearing completion (due Apr 18 for Ahmad). Waleed’s #4 Quotable Labor also targeted for this window. Daniel should confirm #4 status before Sprint 4 starts.

## Sprint 4: Apr 17 – Apr 23 — Job Completion & Mechanic Dashboard

Goal: Close the job lifecycle. Mechanic dashboard live. Job actuals form.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.9 | Job Actuals Input Form | 5 | P0 | Fri–Mon (Apr 17–20) |
| 2.12 | Mechanic Dashboard (Role-Specific) | 5 | P0 | Mon–Wed (Apr 20–22) |
| 2.15 | Mechanic: Complete Job Actuals View | 3 | P0 | Wed–Thu (Apr 22–23) |

Mon Apr 20 meeting: Job actuals form working. Pre-filled estimates, parts section.

Thu Apr 23 meeting: Mechanic dashboard live. Complete Job → actuals form flow.

⚠ DEPENDENCY: 2.9 variance calculation needs Waleed’s #4 Quotable Labor times. If #4 is not wired by Apr 17, build the actuals form and variance UI with placeholder baseline. Wire real pipeline data when available. This does NOT block the ticket — the form and workflow ship regardless.

✓ Unblocks Waleed: Job completion flow (2.9/2.12) ships this sprint. Waleed needs it for mechanic verification in W4 (May 12). 3-week buffer. No risk.

## Sprint 5: Apr 24 – Apr 30 — Admin Pages (Core)

Goal: Admin route group, dashboard home, shop onboarding from admin, all-shops view.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 5.1* | Admin middleware + /admin route group | 0.5 | P0 | Fri (Apr 24) |
| 5.2 | Admin Dashboard Home | 3 | P0 | Fri–Sun (Apr 24–26) |
| 5.3 | Shop Onboarding: Create Shop + Invite Owner | 5 | P0 | Sun–Tue (Apr 26–28) |
| 5.4 | All Shops Management View | 3 | P0 | Tue–Thu (Apr 28–30) |

Mon Apr 27 meeting: Admin dashboard with metrics. Admin can create a shop.

Thu Apr 30 meeting: All Shops view. Test shop created end-to-end via admin.

⚠ Cross-team: Ahmad’s code freeze is Apr 24. Ahmad is in QA from here. No coordination needed from Daniel this sprint.

## Sprint 6: May 1 – May 7 — Admin Complete  ★ ALL P0s DONE

Goal: Finish all remaining admin P0 pages. By end of this sprint, every P0 ticket across both epics is complete.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 5.5 | All Users Management View | 3 | P0 | Fri–Sat (May 1–2) |
| 5.6 | All Bookings Management View | 3 | P0 | Sat–Mon (May 2–4) |
| 5.7 | Booking Detail & Admin Actions | 3 | P0 | Mon–Tue (May 4–5) |
| 5.8 | Vehicle Specs Review Queue | 5 | P0 | Tue–Thu (May 5–7) |

Mon May 4 meeting: Users + bookings views. Admin can look up any booking.

Thu May 7 meeting: ALL P0 TICKETS COMPLETE. Review queue operational.

✓ Dependency cleared: 5.8 requires Waleed’s #2 (confidence) and #5 (source tracking). #5 is DONE. #2 was due Apr 2. Should be long cleared by now.

## Sprint 7: May 8 – May 14 — P1 Tickets

Goal: Ship P1 features in priority order. Ahmad’s consumer app hits his internal May 14 milestone this week.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.16 | Shop Settings & Profile Edit | 3 | P1 | Fri–Sat (May 8–9) |
| 2.11 | Booking History & Service Records | 3 | P1 | Sat–Mon (May 9–11) |
| 2.13 | Mechanic: My Customers View | 3 | P1 | Mon–Tue (May 11–12) |
| 2.14 | Mechanic: My Ratings & Reviews | 2 | P1 | Tue–Wed (May 12–13) |
| -- | Consumer app bug fixes (from log) | -- | P1 | Wed–Thu (May 13–14) |

Mon May 11 meeting: Settings + booking history done.

Thu May 14 meeting: P1 status check. Ahmad’s consumer app milestone. Begin planning integration testing.

## Sprint 8: May 15 – May 21 — Integration Testing & Polish

Goal: Full end-to-end integration testing across consumer app + shop portal + admin. Fix cross-surface bugs. Polish rough edges.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| 2.10 | Payout & Revenue View (if time) | 3 | P1 | Fri–Sat (May 15–16) |
| 5.9 | Payments & Revenue Overview (if time) | 3 | P1 | Sat–Sun (May 16–17) |
| -- | End-to-end integration testing | -- | P0 | Sun–Thu (May 17–21) |

Integration Test Script

- User books on mobile app → booking appears in shop portal jobs queue

- Shop owner accepts → user gets confirmation, mechanic sees on dashboard

- Mechanic starts job → in_progress across all surfaces

- Mechanic completes + fills actuals → variance runs, payment captures

- Admin sees entire lifecycle → full timeline in booking detail

Mon May 18 meeting: Integration test results. Cross-surface bug list.

Thu May 21 meeting: Bug list reviewed. Scope lock for launch.

⚠ Cross-team: Ahmad’s consumer app has been stable since May 4. Integration testing uses Ahmad’s build. Waleed’s pipeline should be in W5 (source scoring, cleanup). All three surfaces are testable together.

## Sprint 9: May 22 – Jun 1 — QA, Android & Launch

Goal: Final QA pass, Android testing (Daniel’s lane), staging deploy, seed Brooklyn shops, and go-live.

| Ticket | Title | Pts | Pri | Target Days |
| --- | --- | --- | --- | --- |
| -- | Full QA: shop portal (all roles) | -- | P0 | Fri–Sun (May 22–24) |
| -- | Full QA: admin pages | -- | P0 | Sun–Mon (May 24–25) |
| -- | Android testing + fixes | -- | P0 | Mon–Tue (May 25–26) |
| -- | Staging deploy + DNS config | -- | P0 | Tue–Wed (May 26–27) |
| -- | Bug fixes from QA | -- | P0 | Wed–Thu (May 27–28) |
| -- | Seed Brooklyn shops via admin | -- | P0 | Thu–Fri (May 28–29) |
| -- | Final checks + go-live | -- | P0 | Sat–Mon (May 30–Jun 1) |

Mon May 25 meeting: All surfaces on staging. Full walkthrough.

Thu May 28 meeting: Go / no-go. Brooklyn shops seeded over weekend if go.

Mon Jun 1: LAUNCH DAY. All three surfaces live. Brooklyn shops accepting bookings.

# Consumer App: QA & Polish Plan

The consumer app build is Ahmad’s lane and is substantially complete. Daniel’s consumer responsibilities are Android testing and cross-surface integration.

Continuous Testing (Sprints 1–6)

- Tue–Thu: 30–60 min/day testing consumer flows on real device. Log bugs.

- Categorize: Critical / Medium / Low. Don’t fix during portal sprints.

Android (Sprint 9)

- Daniel owns Android per team decision #7.

- Test on Android simulators + real devices. Fix platform-specific issues.

- Ahmad’s references to Android on Apr 3 and Apr 27 should be removed from his doc.

# Full Ticket Status Tracker

## Epic 2: Shop Portal

| # | Title | Pts | Pri | Status | Sprint |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Schema: Shop Users & Role Model | 3 | P0 | Done | Completed |
| 2.2 | Clerk Invite-to-Account Flow + Webhook | 5 | P0 | Done | Completed |
| 2.7 | Schedule Management (Time Slots) | 5 | P0 | Nearly Done | Sprint 1 |
| 2.3 | Portal Auth Isolation & Route Guards | 3 | P0 | In Progress | Sprint 1 |
| 2.4 | Shop Registration & Onboarding Wizard | 8 | P0 | Not Started | Sprint 2 |
| 2.5 | Shop Owner Dashboard | 5 | P0 | Not Started | Sprint 2 |
| 2.6 | Mechanic Profile Mgmt + Invite UI | 5 | P0 | Not Started | Sprint 3 |
| 2.8 | Accept/Decline Jobs Queue | 5 | P0 | Not Started | Sprint 3 |
| 2.9 | Job Actuals Input Form | 5 | P0 | Not Started | Sprint 4 |
| 2.12 | Mechanic Dashboard (Role-Specific) | 5 | P0 | Not Started | Sprint 4 |
| 2.15 | Mechanic: Complete Job Actuals View | 3 | P0 | Not Started | Sprint 4 |
| 2.16 | Shop Settings & Profile Edit | 3 | P1 | Not Started | Sprint 7 |
| 2.11 | Booking History & Service Records | 3 | P1 | Not Started | Sprint 7 |
| 2.13 | Mechanic: My Customers View | 3 | P1 | Not Started | Sprint 7 |
| 2.14 | Mechanic: My Ratings & Reviews | 2 | P1 | Not Started | Sprint 7 |
| 2.10 | Payout & Revenue View | 3 | P1 | Not Started | Sprint 8 |

## Epic 5: Admin Pages (consolidated into shop portal)

| # | Title | Pts | Pri | Status | Sprint |
| --- | --- | --- | --- | --- | --- |
| 5.1* | Admin middleware (collapsed) | 0.5 | P0 | Not Started | Sprint 5 |
| 5.2 | Admin Dashboard Home | 3 | P0 | Not Started | Sprint 5 |
| 5.3 | Shop Onboarding: Create + Invite Owner | 5 | P0 | Not Started | Sprint 5 |
| 5.4 | All Shops Management View | 3 | P0 | Not Started | Sprint 5 |
| 5.5 | All Users Management View | 3 | P0 | Not Started | Sprint 6 |
| 5.6 | All Bookings Management View | 3 | P0 | Not Started | Sprint 6 |
| 5.7 | Booking Detail & Admin Actions | 3 | P0 | Not Started | Sprint 6 |
| 5.8 | Vehicle Specs Review Queue | 5 | P0 | Not Started | Sprint 6 |
| 5.9 | Payments & Revenue Overview | 3 | P1 | Not Started | Sprint 8 |
| 5.10 | Platform Activity Log | 2 | P2 | Not Started | Post-launch |

# Risk Register

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Waleed #4 not ready for Sprint 4 | Medium | Build Job Actuals form and variance UI with placeholder baseline. Wire real pipeline data when Waleed’s #4 ships. The form and workflow ship regardless. This is a data dependency, not a blocker. |
| Onboarding wizard scope creep | Medium | 2.4 is 8 pts. Timebox to 4 days. Core flow only. No Stripe Connect, no logo upload at MVP. |
| Admin pages in 2 sprints | Medium | 8 P0 tickets in Sprints 5–6. Admin pages are functional tables — no design polish. Reuse shadcn/ui components. If 5.8 (Review Queue) is too complex, defer to Sprint 7. |
| Convex schema migration during integration | Medium | Waleed writes to trim_specs, vehicle_configs during Apr 4–24. A migration could break Daniel’s builds. Merge-day windows (decision #4) must be defined before Apr 4. |
| Ahmad’s May 14 creates coordination gap | Low | Ahmad’s May 14 is an internal milestone. Daniel’s integration testing (Sprint 8) uses Ahmad’s stable build. 11-day buffer between Ahmad’s QA sign-off and Daniel’s integration sprint. |
| Android testing compressed | Low | Sprint 9 allocates 2 days for Android. If major issues found, can extend into bug-fix window. Ahmad’s iOS build is the reference. |

# Launch Checklist (Week of May 25)

Infrastructure

- shop.otopair.com deployed (includes /admin/* pages)

- Consumer app on App Store (iOS) + Play Store (Android)

- Convex production environment confirmed

- Clerk production keys secured

Data

- 2–3 Brooklyn shops onboarded via admin

- Each shop has at least 1 mechanic with working account

- Service catalog with real pricing from Waleed’s pipeline

- Shop hours configured

Quality

- End-to-end booking flow tested on real iOS and Android devices

- Shop portal tested on Chrome + Safari

- Integration test script (Section 8) passing

- Empty states and error states reviewed

Team

- All team members can access staging

- Waleed’s pipeline data verified against live shops

- Support playbook for common issues

P0s by May 7. Integration by May 21. Launch June 1.