Daniel — Roadmap & Accountability

Shop portal + admin · Apr 24, 2026 · Code freeze TODAY · P0s done May 7 · Launch Jun 1 (38 days)

TL;DR

Best week of the cycle — Stripe Connect FULLY wired (OAuth + 2 webhooks + Convex sync), Vehicle ID passport screen built first pass, pre/post-job survey flow wired, job actuals draft with labor auto-calc. Three things to be honest about: (1) Saturday EOD = 5 things owed — quote requests rendering, post-merge re-verify, Front Desk role (new tonight), brand color tweak, service-filter on surveys. (2) Stripe scope just shrank — refund / dispute / cancellation UI deleted from your column. Use the recovered time to pull P0s forward. (3) May 7 = all P0 tickets complete. 13 days from today. Audit log + role permissions + mobile-responsive mechanic dashboard are the heavy lifts.

OWED SATURDAY APR 26 EOD — FIRE IS OUT BY SAT NIGHT

- Quote requests from app render correctly in shop portal — wire your end of the app→web pipe with Ahmad's Request Sent UI.

- Re-verify service booking app→web post-merge — worked pre-merge per Apr 23. Confirm it still works after the recent merges.

- Front Desk role (new tonight) — scope it before you build. Permissions + UI surface for the Front Desk persona separate from owner.

- Brand color tweak in theme.ts — slightly darker Otopair blue so auto-contrast renders white text. Communicate the final hex to the team.

- Service-filtered data on pre/post surveys — no fluid fields on tire jobs. Yassin flagged.

OPEN ITEMS + PARKED

| Item | Status | Action |
| --- | --- | --- |
| Front Desk role — scope before build | NEW SCOPE | Added tonight (Apr 23). Define permissions + UI surface separate from owner. Do not start building before scoping. |
| Service-filter logic on pre/post surveys | BEFORE FRZ | Surveys currently show fluid fields on tire rotation. Structure-first was intentional but service-filter logic is owed. |
| Vehicle ID visual styling | YASSIN | Doesn't match Yassin's reference screenshots. Needs design review on Monday — not more solo iteration. |
| Document upload parsing — UI ↔ functionality | BY THU | Wiring owed post-Monday, targeting Thursday per Apr 23 sync. |
| Audit log (actor + timestamp + reason) | NEXT 2 WK | Locked Apr 20. Required for marketplace facilitator obligations + internal review of mechanic-flagged corrections. |

CALENDAR — APR 24 → JUN 1

| Week | Focus | Deliverables |
| --- | --- | --- |
| Apr 24–26 | SATURDAY SPRINT | Quote requests render · Post-merge re-verify · Front Desk role · theme.ts color · Service-filter on surveys |
| Apr 27–May 1 | SPRINT 5 ADMIN | Admin middleware · Dashboard home · Shop onboarding from admin · All Shops view |
| May 2–7 | P0 PUSH | All Users · Bookings · Booking Detail · Vehicle Specs Review Queue · Audit log · Role permissions (owner/front desk/mechanic) |
| May 8–14 | P1 + INTEGRATION | Shop settings · Booking history · Mechanic customers · Ratings · Customer statement field · Mobile-responsive mechanic dashboard |
| May 15–21 | INTEGRATION TEST | Full lifecycle test: book → accept → start → complete → pay across all 3 surfaces · Mechanic verification (Waleed wires in) |
| May 22–Jun 1 | QA + ANDROID + LAUNCH | Staging deploy · Seed Brooklyn shops · Android QA · May 28 go/no-go · Jun 1 LAUNCH |

DEPENDENCIES + DELIVERY READINESS

| ↔ WHO'S WAITING ON WHO. → Ahmad; Quote portal end; Sat EOD — Ahmad's Request Sent needs your portal's render side. → Yassin; Vehicle ID feedback; Visual styling doesn't match reference — review Monday. → Yassin; Park kanban revisit; Yassin to tell you to park until post-launch. → Waleed; Tire autofill wiring; For survey brand/model dropdowns from his tier tables. → Waleed; shop_vehicle_data table; Vehicle ID write-back depends on it. → Waleed; Mechanic verification; Waleed wires into your job-completion flow May 8–14. ← Ahmad; Quote requests rendering; Ahmad's Saturday delivery depends on your end. |  | 🚦 DELIVERY READINESS (toward May 7). Stripe Connect (OAuth + webhooks); GREEN. Vehicle ID passport screen; GREEN. Pre/post-job survey flow; GREEN. Job actuals + complete/reopen; GREEN. Floating job panel + A-shortcut; GREEN. Dashboard polish; GREEN. Quote portal rendering; AMBER. Service-filter on surveys; AMBER. Front Desk role + audit log + roles; RED. Mobile-responsive mechanic dash; RED. |
| --- | --- | --- |

SHIPPED THIS WEEK  +  LOCKED DECISIONS (NO RELITIGATION)

| ✅ SHIPPED THIS WEEK — keep visible. • Stripe Connect FULLY wired — OAuth onboarding, 2 webhooks (platform + connected), Convex sync firing. • Vehicle ID passport screen — first pass (prior-visit data OR empty state). • Pre-job + post-job survey flow wired — full loop vehicle ID → pre-job → start → complete → post-job → close. • Job actuals draft — labor auto-calc, complete/reopen flow. • Floating job detail panel + keyboard shortcut A to accept. • Dashboard polish — hover states, bell removal, panel bleed fix. • SCOPE REMOVED: refund/dispute/cancellation UI — Stripe handles it. |  | 🔒 LOCKED DECISIONS — no relitigation. • Mechanic NEVER quotes — calendar-focused only. Quote alerts → Front Desk + Owner. • First-accept-wins via Convex real-time. Accept button disappears on the other side. • Stripe Express. OAuth onboarding. 2-day rolling payouts. 7% fee customer-facing. Walk-in 0% at MVP. • Mechanic dashboard = mobile-responsive web (NOT native). • Audit log: actor + timestamp + REQUIRED reason. • Pre-job: 3 required + 2 conditional + 1 optional. Post-job: mandatory specs + optional labor calibration. • Source-of-truth: shop > research > default. Mirrors job_actuals confidence pattern. |
| --- | --- | --- |

TOP RISKS

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Front Desk role new scope before code freeze | HIGH | Added Apr 23 PM with no prior scoping. Define permissions + UI surface before building. Do not let it expand silently. |
| May 7 P0 deadline — 13 days, 4+ heavy items | HIGH | Audit log + role permissions + mobile mechanic dash + Vehicle Specs Review Queue. Use the recovered Stripe-UI scope time to pull these forward. |
| Vehicle ID styling + survey service-filter | MED | Yassin flagged both. Vehicle ID needs design review Mon (not solo iteration). Service-filter logic owed before code freeze locks survey shape. |

MONDAY SELF-CHECK (3 MINUTES BEFORE THE MEETING)

1. Saturday five — all 5 landed, or which slipped and why?  2. Front Desk role — scoped before built, or am I building blind?  3. P0 readiness — am I on track for May 7 with audit log + roles + mechanic dash?  4. What am I waiting on (Yassin / Waleed / Ahmad) and have I named it in writing?  5. Did I park kanban revisit, or is it still creeping into my week?